## Slide 1: PLANEAMENTO DE SOFTWARE: PASSWORD MANAGER
Trabalho realizado por:
António Graça [30000497] & Pedro Simões [30007732].

## Slide 2: Introdução: explicação, âmbito e objetivos
Fazendo jus á definição de âmbito (o âmbito de um projecto é um esboço detalhado de todos os aspectos de um projecto, incluindo todas as actividades relacionadas, recursos, prazos e prestações, bem como os limites do projecto), sendo o do nosso projecto, obrigatoriamente, a implementação de uma infraestrutura tecnológica (hardware, software, tecnologias de armazenamento de dados, tecnologias de rede e telecomunicações) e o seu respectivo desenvolvimento; nomeadamento a execução de um password manager (com suporte para autenticação de dois passos e para pagamentos seguros).

## Slide 6
2. Analysis/Software Requirements
3. Design
4. Team Training
5. Development
6. Testing
7. Training
8. Documentation
9. Maintenance Team Training
10. Pilot
11. Deployment
12. Post Implementation Review
Software Development Plan
1. Scope
WBS: Work
Breakdown
Structure
Notes: (Incluí a descrição de atividades, e sua sequência)

## Slide 7
1. Scope
1.1. Determine project scope
1.2. Secure project sponsorship
1.3. Define preliminary resources
1.4. Secure core resources
1.

## Slide 8
2. Analysis/Software Requirements
2.1. Conduct needs analysis
2.2. Draft preliminary software specifications
2.3. Develop preliminary budget
2.4. Review software specifications/budget with team
2.5. Incorporate feedback on software specifications
2.6. Develop delivery timeline
2.7. Obtain approvals to proceed (concept, timeline, budget)
2.8. Secure required resources
2.

## Slide 9
3. Design
3.1. Review preliminary software specifications
3.2. Develop functional specifications
3.3. Develop prototype based on functional specifications
3.4. Review functional specifications
3.5. Incorporate feedback into functional specifications
3.6. Obtain approval to proceed
3.

## Slide 10
4. Team Training
4.1. Framework & Environment training and specification
4.2. Language training
4.3. Methodology and work structure
4.

## Slide 11
5. Development
5.1. Review functional specifications
5.2. Identify modular/tiered design parameters
5.3. Assign development staff
5.5. Developer testing (primary debugging)
5.4. Develop code
5.

## Slide 12
5.4. Develop code
5.4.1. Base App Framework
5.4.2. API Definition
5.4.3. Authentication System Definition
5.4.4. Security Protocol Definitions
5.4.5. Design Language Definition
5.4.6. Encryption Methodology Definition
5.4.7. Two-Step Authentication
5.4.8. Password Management
5.4.9. Secure Payment Support
5.4.

## Slide 13
5.4.7. Two-Step Authentication
5.4.7.1. Two-Step Via App
5.4.7.2. Two-Step Via SMS
5.4.7.3. Two-Step Via Email
5.4.7.4. User's Interface Design
5.4.8. Password Management
5.4.8.1. Database Definition & Implementation
5.4.8.2. Encryption Services Backend Implementation
5.4.8.3. User Data Insertion & Treatment
5.4.8.4. Final Secure Password Manager Protocols
5.4.8.5. User's Interface Design
5.4.9. Secure Payment Support
5.4.9.1. Services Setup
5.4.9.2. Final Protocols Implementation
5.4.9.3. User's Interface Design
5.4.7. & 5.4.8. & 5.4.9.

## Slide 14
6. Testing
6.1. Develop unit test plans using product specifications
6.3.1. Unit Testing: Review modular code
6.3.2. Unit Testing: Test component modules to product specifications
6.3.3. Unit Testing: Identify anomalies to product specifications
6.3.4. Unit Testing: Modify code
6.3.5. Unit Testing: Re-test modified code
6.4.1. Integration Testing: Test module integration
6.4.3. Integration Testing: Modify code
6.4.4. Integration Testing: Re-test modified code
6.4.2. Integration Testing: Identify anomalies to specifications
6.2. Develop integration test plans using product specifications
6.

## Slide 15
7. Training
7.1. Develop training specifications for end users
7.2. Develop training specifications for helpdesk support staff
7.3. Identify training delivery methodology (computer based training, classroom, etc.)
7.4. Develop training materials
7.5. Conduct training usability study
7.6. Finalize training materials
7.7. Develop training delivery mechanism
7.

## Slide 16
8. Documentation
8.1. Develop Help specification
8.2. Develop Help system
8.3. Review Help documentation
8.4. Incorporate Help documentation feedback
8.5. Develop user manuals specifications
8.6. Develop user manuals
8.7. Review all user documentation
8.8. Incorporate user documentation feedback
8.

## Slide 17
10. Pilot
10.1. Identify test group
10.2. Develop software delivery mechanism
10.3. Install/deploy software
10.4. Obtain user feedback
10.5. Evaluate testing information
10.

## Slide 18
11. Deployment
11.1. Determine final deployment strategy
11.2. Develop deployment methodology
11.3. Secure deployment resources
11.4. Train support staff
11.5. Deploy software
11.

## Slide 19
12. Post Implementation Review
12.1. Document lessons learned
12.2. Distribute to team members
12.3. Create software maintenance team
12.

## Slide 20: Descrição, Sequência de actividades & Folgas
Slack (folga), é a quantidade de tempo que uma tarefa pode deslizar antes de colidir com outra tarefa. E pode ser utilizado como tempo de reserva, se necessário, quando a sua planificação estiver em risco de ser atrasada.

## Slide 25: Recursos e Afetação

## Slide 30: Matriz de Risco
...é uma ferramenta de gestão de riscos que permite de forma visual identificar quais são os riscos que devem receber mais atenção.

## Slide 32: Matriz de STAKEHOLDERS
...é uma ferramenta que permite identificar cada um dos intervenientes na empresa dependendo do tipo de característica que possui. Graças à matriz, é possível conhecer o tipo de influência que cada parte interessada pode exercer sobre o negócio.

## Slide 34: EVM: EARNED VALUE MANAGEMENT
EAC: €10,182.04; O valor do trabalho realizado, também denominado de custo orçamentado do trabalho realizado (EV - Earned Value ou BCWP - Budgeted Cost Of Work Performed), é a percentagem do orçamento total, igual à percentagem do trabalho realmente concluído.
ACWP: €8,263.59; O custo real, também chamado de custo real do trabalho realizado (AC – Actual Cost ou ACWP - Actual Cost of Work Performed), é o total dos custos diretos e indiretos necessários à realização do trabalho efetivo durante um dado período.
BCWP: €94,763.59; O orçamento, também denominado custo orçamentado do trabalho programado (PV - Planned Value ou BCWS-Budgeted Cost of Work Scheduled), é a estimativa do custo planeado e aprovado para ser consumido durante um determinado período.

## Slide 36: Dependências DAS ACTIVIDADES

## Slide 37: Dependências DAS ACTIVIDADES

## Slide 41: PERT-CPM
O PERT (Program Evaluation and Review Technique) é um método muito utilizado na construção do planeamento dos projectos; PERT e CPM utilizam principalmente os conceitos de Redes ou grafos para planear e visualizar a ligação entre as atividades do projecto.

## Slide 43: SIMULAÇÃO A 50%

## Slide 44: SIMULAÇÃO A 50%: WORK STATS
Chart: Work (hrs)
| Scope | Analysis/Software Requirements | Design | Team Training | Development | Testing | Training | Documentation | Maintenance Team Training | Pilot | Deployment | Post Implementation Review | Development Complete
Actual Work | 14 | 60 | 60 | 25.5 | 374.5 | 140 | 108 | 118 | 40 | 36 | 20 | 12 | 0
Remaining Work | 14 | 60 | 60 | 25.5 | 374.5 | 140 | 108 | 118 | 40 | 36 | 20 | 12 | 0
Baseline Work | 28 | 120 | 120 | 51 | 749 | 280 | 216 | 236 | 80 | 72 | 40 | 24 | 0

## Slide 45: SIMULAÇÃO A 50%: WORK STATS
Chart: 
| Management | Project Manager | Analyst | Developer | Tester | Trainer | Technical Writer | Deployment Team | Team-Training Team
Actual Work | 22 | 51.5 | 82 | 394.5 | 140 | 108 | 118 | 52 | 40
Remaining Work | 22 | 51.5 | 82 | 394.5 | 140 | 108 | 118 | 52 | 40

## Slide 46: SIMULAÇÃO A 50%: VARIANCE OVER TIME
Chart: 
| '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23
CV | -1741.0714 | -2812.5 | -3000 | -3405.464 | -4359.497 | -5313.5299 | -6213.8687 | -12953.6289 | -14443.3891 | -15933.1494 | -17917.1653 | -21387.4451 | -24857.7248 | -28328.0045 | -28328.0045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SV | -84.24 | -186.84 | -315.09 | -475.14 | -577.74 | -667.02 | -874.3 | -1152.415 | -1152.415 | -1152.415 | -1202.815 | -1202.815 | -1370.815 | -1421.215 | -1488.415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 47: SIMULAÇÃO A 50%: INDICE OVER TIME
Chart: 
| '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23
SPI | 0.60755 | 0.55498 | 0.51192 | 0.50268 | 0.50221 | 0.5182 | 0.56113 | 0.5 | 0.5 | 0.5 | 0.5 | 0.53264 | 0.5 | 0.51155 | 0.51104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPI | 0.069683 | 0.076509 | 0.099229 | 0.1236 | 0.11793 | 0.11896 | 0.15247 | 0.081697 | 0.073893 | 0.06745 | 0.062909 | 0.060234 | 0.052264 | 0.049919 | 0.052056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 48: SIMULAÇÃO A 50%: REMAINING AVAILABILITY
Chart: 
| 21/08/22 | 04/09/22 | 18/09/22 | 02/10/22 | 16/10/22 | 30/10/22 | 13/11/22 | 27/11/22 | 11/12/22 | 25/12/22 | 08/01/23 | 22/01/23 | 05/02/23 | 19/02/23 | 05/03/23 | 19/03/23 | 02/04/23 | 16/04/23
Remaining Availability (Management) | 68 | 76 | 71 | 53 | 80 | 72 | 80 | 64 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
Remaining Availability (Project Manager) | 64 | 32 | 80 | 57 | 80 | 72 | 80 | 64 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 56
Remaining Availability (Analyst) | 111 | 116 | 89 | 144 | 160 | 144 | 160 | 128 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160
Remaining Availability (Developer) | 400 | 400 | 400 | 360 | 400 | 296 | 320 | 256 | 320 | 267 | 288 | 280 | 320 | 344 | 400 | 400 | 400 | 400
Remaining Availability (Tester) | 240 | 240 | 240 | 152 | 240 | 216 | 240 | 192 | 240 | 240 | 240 | 240 | 240 | 176 | 160 | 168 | 240 | 240
Remaining Availability (Trainer) | 240 | 240 | 240 | 152 | 240 | 216 | 240 | 192 | 240 | 240 | 240 | 240 | 240 | 176 | 160 | 232 | 240 | 240
Remaining Availability (Technical Writer) | 160 | 160 | 160 | 120 | 160 | 144 | 160 | 128 | 160 | 160 | 160 | 112 | 24 | 132 | 160 | 160 | 160 | 160
Remaining Availability (Deployment Team) | 400 | 392 | 400 | 360 | 400 | 360 | 400 | 320 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 392 | 320 | 392
Remaining Availability (Team-Training Team) | 320 | 320 | 320 | 248 | 320 | 288 | 320 | 256 | 320 | 320 | 320 | 320 | 320 | 280 | 320 | 320 | 320 | 320

## Slide 49: SIMULAÇÃO A 50%: MILESTONES
Chart: 

## Slide 50: SIMULAÇÃO A 50%: LAST TASKS
Chart: 
| Status: On Schedule | Status: Late | Status: Future Task
Work | 60 | 647 | 1309

## Slide 51: SIMULAÇÃO A 50%: COST STATUS
Chart: 
| Scope | Analysis/Software Requirements | Design | Team Training | Development | Testing | Training | Documentation | Maintenance Team Training | Pilot | Deployment | Post Implementation Review | Development Complete
Actual Cost | 1584.24 | 1811.94 | 336.78 | 5363.615 | 16822.9 | 2807.2 | 2618.28 | 1809.16 | 169.4 | 13909.72 | 87 | 61.56 | 0
Remaining Cost | 1584.24 | 1811.94 | 336.78 | 27363.615 | 16822.9 | 2807.2 | 2618.28 | 1809.16 | 169.4 | 13909.72 | 87 | 61.56 | 0
Baseline Cost | 3168.48 | 3623.88 | 673.56 | 32727.23 | 33645.8 | 5614.4 | 5236.56 | 3618.32 | 338.8 | 27819.44 | 174 | 123.12 | 0

## Slide 52: SIMULAÇÃO A 50%: COST DISTRIBUTION
Chart: 
| Status: On Schedule | Status: Late | Status: Future Task
Cost | 252 | 2976.83 | 5034.76

## Slide 53: SIMULAÇÃO A 50%: COST DETAILS

## Slide 54: SIMULAÇÃO A 100%

## Slide 55: SIMULAÇÃO A 100%: WORK STATS
Chart: Work (hrs)
| Scope | Analysis/Software Requirements | Design | Team Training | Development | Testing | Training | Documentation | Maintenance Team Training | Pilot | Deployment | Post Implementation Review | Development Complete
Actual Work | 28 | 120 | 120 | 51 | 749 | 280 | 216 | 236 | 80 | 72 | 40 | 24 | 0
Remaining Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baseline Work | 28 | 120 | 120 | 51 | 749 | 280 | 216 | 236 | 80 | 72 | 40 | 24 | 0

## Slide 56: SIMULAÇÃO A 100%: WORK STATS
Chart: 
| Management | Project Manager | Analyst | Developer | Tester | Trainer | Technical Writer | Deployment Team | Team-Training Team
Actual Work | 44 | 103 | 164 | 789 | 280 | 216 | 236 | 104 | 80
Remaining Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 57: SIMULAÇÃO A 100%: VARIANCE OVER TIME
Chart: 
| '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23
CV | -3241.0714 | -4312.5 | -5383.9286 | -6405.464 | -7359.497 | -8313.5299 | -9213.8687 | -21203.6289 | -22693.3891 | -24183.1494 | -26167.1653 | -29637.4451 | -33107.7248 | -36578.0045 | -39354.2282 | -42130.452 | -45600.7317 | -49071.0114 | -52541.2912 | -56011.5709 | -59481.8506 | -62952.1303 | -66422.41 | -69892.6897 | -73362.9694 | -76833.2491 | -79068.8851 | -80404.2052 | -81739.5253 | -83074.8453 | -84253.1316 | -85355.1605 | -86309.1934 | -86500 | -86500
SV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 58: SIMULAÇÃO A 100%: INDICE OVER TIME
Chart: 
| '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '22 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23 | '23
SPI | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
CPI | 0.062114 | 0.088719 | 0.10707 | 0.1298 | 0.13622 | 0.14276 | 0.17778 | 0.098043 | 0.0922 | 0.087014 | 0.084193 | 0.079899 | 0.076476 | 0.073685 | 0.071796 | 0.07015 | 0.068368 | 0.066833 | 0.06696 | 0.067788 | 0.068519 | 0.067315 | 0.067555 | 0.068915 | 0.07034 | 0.070926 | 0.073635 | 0.078166 | 0.080058 | 0.081882 | 0.082696 | 0.083315 | 0.084164 | 0.085678 | 0.087202

## Slide 59: SIMULAÇÃO A 100%: REMAINING AVAILABILITY
Chart: 
| 21/08/22 | 04/09/22 | 18/09/22 | 02/10/22 | 16/10/22 | 30/10/22 | 13/11/22 | 27/11/22 | 11/12/22 | 25/12/22 | 08/01/23 | 22/01/23 | 05/02/23 | 19/02/23 | 05/03/23 | 19/03/23 | 02/04/23 | 16/04/23
Remaining Availability (Management) | 68 | 76 | 71 | 53 | 80 | 72 | 80 | 64 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
Remaining Availability (Project Manager) | 64 | 32 | 80 | 57 | 80 | 72 | 80 | 64 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 56
Remaining Availability (Analyst) | 111 | 116 | 89 | 144 | 160 | 144 | 160 | 128 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160
Remaining Availability (Developer) | 400 | 400 | 400 | 360 | 400 | 296 | 320 | 256 | 320 | 267 | 288 | 280 | 320 | 344 | 400 | 400 | 400 | 400
Remaining Availability (Tester) | 240 | 240 | 240 | 152 | 240 | 216 | 240 | 192 | 240 | 240 | 240 | 240 | 240 | 176 | 160 | 168 | 240 | 240
Remaining Availability (Trainer) | 240 | 240 | 240 | 152 | 240 | 216 | 240 | 192 | 240 | 240 | 240 | 240 | 240 | 176 | 160 | 232 | 240 | 240
Remaining Availability (Technical Writer) | 160 | 160 | 160 | 120 | 160 | 144 | 160 | 128 | 160 | 160 | 160 | 112 | 24 | 132 | 160 | 160 | 160 | 160
Remaining Availability (Deployment Team) | 400 | 392 | 400 | 360 | 400 | 360 | 400 | 320 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 392 | 320 | 392
Remaining Availability (Team-Training Team) | 320 | 320 | 320 | 248 | 320 | 288 | 320 | 256 | 320 | 320 | 320 | 320 | 320 | 280 | 320 | 320 | 320 | 320

## Slide 60: SIMULAÇÃO A 100%: MILESTONES
Chart: 

## Slide 61: SIMULAÇÃO A 100%: LAST TASKS
Chart: 
| Status: Complete
Work | 2016

## Slide 62: SIMULAÇÃO A 100%: COST STATUS
Chart: 
| Scope | Analysis/Software Requirements | Design | Team Training | Development | Testing | Training | Documentation | Maintenance Team Training | Pilot | Deployment | Post Implementation Review | Development Complete
Actual Cost | 3168.48 | 3623.88 | 673.56 | 10727.23 | 33645.8 | 5614.4 | 5236.56 | 3618.32 | 338.8 | 27819.44 | 174 | 123.12 | 0
Remaining Cost | 0 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baseline Cost | 3168.48 | 3623.88 | 673.56 | 32727.23 | 33645.8 | 5614.4 | 5236.56 | 3618.32 | 338.8 | 27819.44 | 174 | 123.12 | 0

## Slide 63: SIMULAÇÃO A 100%: COST DISTRIBUTION
Chart: 
| Status: Complete
Cost | 8263.59

## Slide 64: SIMULAÇÃO A 100%: COST DETAILS

## Slide 65: SIMULAÇÃO A 100%: TASK COST VARIANCE
Chart: 
| Scope | Analysis/Software Requirements | Design | Team Training | Development | Testing | Training | Documentation | Maintenance Team Training | Pilot | Deployment | Post Implementation Review | Development Complete
Cost Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 66: SIMULAÇÃO A 100%: TASK COST VARIANCE DETAILS

## Slide 67: SIMULAÇÃO A 100%: RESOURCE COST VARIANCE
Chart: 
| Management | Project Manager | Analyst | Developer | Tester | Trainer | Technical Writer | Deployment Team | Team-Training Team | Server | Workstation | Projector | Editor License
Cost Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 68: SIMULAÇÃO A 100%: RESOURCE COST VARIANCE DETAILS